## Action Plan
# | Task | Category | Priority | Status | Owner | Notes
1 | Finish Google Business Profile video verification | Local SEO | P1 | WAITING ON YOU | Roberto | Film at 4200 Keller Haslet Rd: surroundings + branded gear + WP admin login. One continuous take in Google's flow.
2 | Add 10 remaining GBP service areas | Local SEO | P1 | WAITING ON YOU | Roberto | After verification: Edit profile > Location and areas. Add: Watauga, Roanoke, Justin, Saginaw, Northlake, Westlake, Trophy Club, Argyle, Colleyville, Arlington. ~2 min.
3 | Update GBP phone to (817) 546-5994 | Local SEO | P1 | QUEUED (CLAUDE) | Claude | After verification clears. Also add photos, hours, description.
4 | Bing Places - Import from Google | Citations | P1 | QUEUED (CLAUDE) | Claude+Roberto | One-click import after GBP verified. Roberto logged in, Claude drives.
5 | Start review engine - first 10 Google reviews | Local SEO | P1 | TO DO | Roberto | Text parents the review link after practice (get link from GBP dashboard). Script in Email Playbook doc.
6 | Yelp business listing (ONE listing, no lists) | Citations | P2 | QUEUED (CLAUDE) | Claude+Roberto | NAP: Joga Labs / (817) 546-5994 / jogalab.com. SAB - hide address.
7 | Facebook page - update NAP + link | Citations | P2 | WAITING ON YOU | Roberto | Current FB is facebook.com/soccertalk - rename to Joga Labs or create new page; set (817) 546-5994 + jogalab.com.
8 | Apple Maps (mapsconnect.apple.com) | Citations | P2 | TO DO | Roberto | Powers Siri/iPhone "near me". Free.
9 | Nextdoor business page | Citations | P2 | TO DO | Roberto | Neighborhoods = exactly your service areas.
10 | US Youth Futsal / United Futsal member club listing | Backlinks | P2 | TO DO | Roberto | Governing-body directory link. Sport-relevant backlink few competitors have.
11 | Keller Chamber of Commerce membership | Backlinks | P2 | TO DO | Roberto | Directory backlink + local networking. Also consider Northwest Metroport Chamber.
12 | Ask Chaos Sports Performance + LeagueLobster to hyperlink Joga Labs | Backlinks | P1 | TO DO | Roberto | Easiest high-value links. Email/ask at next game.
13 | Press pitch to Community Impact (Keller edition) | Backlinks | P1 | TO DO | Roberto | Template ready in Email Playbook doc. Angle: Brazilian ex-pro + autism soccer program.
14 | Macaroni KID / Hulafrog event listings for tryouts | Citations | P3 | TO DO | Roberto | Each event listing links back to jogalab.com.
15 | Sponsor a Keller ISD school event / local 5K | Backlinks | P3 | TO DO | Roberto | Sponsor logo + link on .org/school pages.
16 | Build "DFW Futsal & Indoor Facility Guide" page (linkable asset) | Content | P2 | QUEUED (CLAUDE) | Claude | Researched guide page in site design. Targets "indoor soccer near me" + earns organic links.
17 | Upload llms.txt to site root via FileZilla | Technical SEO | P2 | WAITING ON YOU | Roberto | File is in GitHub repo. Drag to public_html root so jogalab.com/llms.txt resolves.
18 | Weekly match recap posts on site | Content | P2 | TO DO | Roberto+Claude | After each game weekend. Claude can draft from LeagueLobster results.
19 | MailerLite: build forms + swap into site | Email | P2 | QUEUED (CLAUDE) | Claude+Roberto | Send Claude the embed codes; groups per Email Playbook.
20 | Team parent email flow live (pre-game / post-game) | Email | P1 | TO DO | Roberto+Claude | Templates + automation options in Email Playbook doc.
21 | Keep TextNow number active (weekly use!) | Operations | P1 | TO DO | Roberto | Free TextNow numbers are reclaimed after ~2 weeks idle. Losing it breaks NAP everywhere.
22 | Upload training video to WordPress home gallery | Website | P3 | QUEUED (CLAUDE) | Roberto | WP Media Library accepts large files; then Claude re-adds gallery item.
23 | Request indexing in Search Console for /futsal-teams/ + city pages | Technical SEO | P2 | TO DO | Roberto | URL Inspection > Request Indexing. Sitemap already resubmitted.
24 | Monthly SEO check-in (Search Console + GBP stats) | Measurement | P3 | TO DO | Roberto+Claude | 15 min/month. Watch "futsal keller", "futsal near me" positions.
25 | Collect testimonials + add Review markup to site (after 10 real reviews) | Local SEO | P3 | QUEUED (CLAUDE) | Claude | Legitimate star strategy - see SEO-PLAN.md.
LEGEND - edit the Status column as you go:
| DONE | Completed
| IN PROGRESS | Currently being worked
| WAITING ON YOU | Needs your action to proceed
| TO DO | Not started
| QUEUED (CLAUDE) | Claude will do it - just say the word in chat

## Citations - NAP
Directory | URL | Status | Notes
OFFICIAL NAP (use EXACTLY this everywhere)
Name | Joga Labs
Phone | (817) 546-5994
Email | info@jogalabs.com
Website | https://jogalab.com
Type | Service Area Business (hide address) |  | Service areas: Keller, Fort Worth, Haslet, Watauga, Roanoke, Justin, Saginaw, Northlake, Westlake, Trophy Club, Argyle, Colleyville, Arlington
Google Business Profile | business.google.com | IN PROGRESS | Awaiting video verification
Bing Places | bingplaces.com | TO DO | Import from Google after verification
Apple Maps | mapsconnect.apple.com | TO DO
Yelp | biz.yelp.com | TO DO | Single listing only
Facebook | facebook.com | TO DO | Update page NAP
Nextdoor | nextdoor.com | TO DO
Alignable | alignable.com | TO DO
Macaroni KID Fort Worth | fortworth.macaronikid.com | TO DO | Post tryouts as events
Hulafrog Keller | hulafrog.com | TO DO
US Youth Futsal | usyouthfutsal.com | TO DO | Member club directory
Keller Chamber | kellerchamber.com | TO DO | Paid membership

## Weekly Routine
When | Task | Time | Why
Game day morning | Send pre-game email to parents (template in Playbook) | 5 min | Attendance + parent engagement
After each game | Enter result note; send post-game email; post recap on site | 15 min | Fresh content = SEO + community
After practice (1x/week) | Text 2-3 parents the Google review link | 2 min | Stars on your profile
Weekly | Send/receive one text on the TextNow number | 1 min | Keeps the number alive
Monthly | Check Search Console queries + GBP calls/clicks; tell Claude the numbers | 15 min | Measure what is working